## Overview
YouTube Tools Hub — UPDATED Blog Publish Plan 2026
Generated | 2026-07-19
Site | https://www.youtubetoolshub.com
BASELINE REALITY (do not ignore)
Live blog posts in code | 95
Live tools in code | 27
Current traffic reality | Low hundreds of weekly views — plan for growth, not 60k month-1 fantasy
THIS PLAN
New posts planned | 36
Cadence | 3 new posts/week + 1 refresh/week (12 weeks)
Waves | 1 Money/CPC → 2 Tool traffic → 3 Commercial software/gear → 4 Growth → 5 Niches → 6 Authority
Primary monetization | AdSense (Tier-1 intent) + tool engagement; affiliate later
Avg target | Higher CPC topics first; high-volume tool posts second
SUCCESS METRICS (track weekly in GSC + AdSense)
GSC clicks | Baseline → +50% in 90 days if publishing + deploy done
Page RPM | Target move toward $3–$6 as US share rises
Top pages | Earnings calculator, CPM rates, media kit, thumbnail downloader, new money posts
SHEETS IN THIS FILE
Overview | This summary
New Posts Queue | All new articles to publish (36)
12-Week Calendar | Week-by-week Mon/Wed/Fri style schedule
Refresh Queue | Improve existing URLs (do not create duplicates)
Tool CTA Map | Every post → primary tool
Do Not Publish | Topics to skip or delay
Live Inventory Snapshot | Current blog slugs (avoid cannibalization)
Writing Rules | SEO/AEO/GEO definition of done

## New Posts Queue
ID | Wave | Week | Priority | Title | Primary Keyword | Secondary Keywords | Intent | US Vol (dir.) | Est CPC $ | Est Page RPM $ | Cluster | Primary Tool CTA | Secondary Tools / Links | Format | Words Target | FAQ Count | Why This Post | Avoid Overlap | Status | Publish Date | Live URL | Notes
W1-01 | 1 | 1 | P0 | YouTube Sponsorship Rates 2026: How Much Brands Pay Creators | youtube sponsorship rates | youtube brand deal rates, creator sponsorship pricing, youtube sponsorship calculator | commercial | 2K–8K | $6–$14 | $4–$10 | monetization | /tools/youtube-earnings-calculator | /tools/youtube-engagement-rate-calculator; /resources/youtube-cpm-rates | Data guide + rate ranges by size + pitch tips | 2500 | 8 | High commercial intent; brands + creators; strong AdSense categories | Do not rewrite existing sponsorship-guidelines post—extend rates/data angle | todo
W1-02 | 1 | 1 | P0 | YouTube AdSense RPM Optimization: 12 Ways to Raise Revenue Per 1,000 Views | youtube rpm optimization | increase youtube rpm, improve adsense rpm, youtube revenue per mille | commercial | 1K–5K | $5–$12 | $4–$9 | monetization | /tools/youtube-earnings-calculator | /resources/youtube-cpm-rates; /blog/youtube-rpm-vs-cpm-explained | Action checklist + country/niche levers | 2400 | 8 | Direct money keyword; pairs with calculator for dwell time | Link existing RPM vs CPM + CPM rates; do not duplicate them | todo
W1-03 | 1 | 1 | P0 | YouTube Media Kit Examples 2026: 7 Templates Brands Actually Open | youtube media kit examples | creator media kit samples, influencer media kit example, youtube press kit | commercial | 1K–4K | $4–$11 | $3–$8 | monetization | /tools/youtube-engagement-rate-calculator | /blog/youtube-media-kit-template-2026; /tools/youtube-earnings-calculator | Examples + copy blocks; link existing template post | 2200 | 6 | Sponsorship intent; complements existing media kit template | Existing youtube-media-kit-template-2026 is the pillar—this is examples spin | todo
W1-04 | 1 | 2 | P0 | Best YouTube Affiliate Programs 2026 (High Commission, Creator-Friendly) | best youtube affiliate programs | youtube affiliate marketing, high commission affiliate youtube, best affiliate programs for youtubers | commercial | 3K–10K | $5–$13 | $4–$10 | monetization | /tools/youtube-video-ideas-generator | /tools/youtube-earnings-calculator; /resources/youtube-monetization-guide | List + criteria table + disclosure best practices | 2800 | 8 | High CPC commercial + affiliate upside beyond AdSense | New angle; not a clone of monetization guide | todo
W1-05 | 1 | 2 | P0 | How Much Do YouTubers Make Per Video in 2026? (Views × RPM Examples) | how much do youtubers make per video | youtube earnings per video, how much money per youtube video, youtube video revenue | informational-commercial | 5K–15K | $3–$8 | $3–$7 | monetization | /tools/youtube-earnings-calculator | /resources/youtube-cpm-rates; /blog/how-much-youtube-pays-per-1000-views-2026 | Scenario tables by views/RPM/country | 2300 | 8 | High search demand; calculator CTA converts | Differentiate from pay-per-view and 1M views posts with per-video framing | todo
W1-06 | 1 | 2 | P1 | YouTube Brand Deal Email Template: Outreach That Gets Replies | youtube brand deal email template | sponsorship email template, pitch brands on youtube, creator outreach email | commercial | 1K–4K | $4–$10 | $3–$8 | monetization | /tools/youtube-engagement-rate-calculator | /blog/youtube-media-kit-template-2026; /blog/youtube-sponsorship-guidelines-2026 | 3 copy-paste emails + when to send | 2000 | 6 | High intent commercial; sponsorship ecosystem | Complements sponsorship guidelines | todo
W2-01 | 2 | 3 | P0 | YouTube Thumbnail Size 2026: Exact Specs, Safe Zones & File Rules | youtube thumbnail size | youtube thumbnail dimensions, 1280x720 thumbnail, youtube thumbnail resolution | informational | 10K–50K | $0.80–$2.50 | $1.50–$4 | thumbnails | /tools/youtube-thumbnail-downloader | /tools/youtube-ai-thumbnail-generator; /tools/youtube-thumbnail-generator | Spec table + mistakes + tool CTAs | 2000 | 8 | Huge evergreen volume; feeds thumbnail tools | Refresh if thin older thumbnail posts exist—keep one canonical | todo
W2-02 | 2 | 3 | P0 | How to Download a YouTube Thumbnail in Highest Quality (HD/4K) | how to download youtube thumbnail | download youtube thumbnail hd, save youtube thumbnail, youtube thumbnail grabber | informational | 10K–50K | $0.70–$2.20 | $1.50–$3.50 | thumbnails | /tools/youtube-thumbnail-downloader | /tools/thumbnail-tools; /blog/how-to-optimize-youtube-thumbnails | Step-by-step HowTo + legal note | 1800 | 7 | Massive intent match for #1 free tool | Canonical how-to for the downloader tool | todo
W2-03 | 2 | 3 | P1 | YouTube Description Template 2026: Copy, Customize, Rank | youtube description template | youtube description examples, best youtube description format, youtube description structure | informational | 2K–8K | $1.50–$4.50 | $2–$5 | seo | /tools/youtube-description-generator | /tools/youtube-timestamp-generator; /tools/youtube-tag-generator | 3 templates (tutorial/review/vlog) + SEO rules | 2200 | 7 | Template intent + description tool funnel | Avoid repeating full SEO checklist—link it | todo
W2-04 | 2 | 4 | P0 | YouTube Chapters Template: Timestamp Format That Works in 2026 | youtube chapters template | youtube timestamps template, how to add chapters youtube, youtube chapter format | informational | 2K–8K | $1–$3.50 | $1.50–$4 | seo | /tools/youtube-timestamp-generator | /tools/youtube-description-generator | Copy-paste templates + rules (0:00) | 1800 | 7 | Direct tool match; easy featured snippet | Pairs with timestamp tool expanded content | todo
W2-05 | 2 | 4 | P1 | YouTube Channel Name Ideas: Framework by Niche (With Generator Workflow) | youtube channel name ideas | youtube name generator, cool youtube names, youtube channel names 2026 | informational | 10K–40K | $1–$3.50 | $1.50–$4 | growth | /tools/youtube-channel-name-generator | /tools/youtube-niche-finder-quiz; /tools/youtube-banner-logo-maker | Framework + niche lists + tool CTA | 2400 | 7 | Huge volume; new-channel funnel | Make unique vs any existing name posts | todo
W2-06 | 2 | 4 | P1 | YouTube Tags Explained 2026: How Many Tags, What Works, What Doesn’t | youtube tags | how many youtube tags, youtube tags best practices, youtube video tags 2026 | informational | 5K–20K | $1–$3 | $1.50–$4 | seo | /tools/youtube-tag-generator | /tools/youtube-tag-extractor; /tools/seo-tools | Myths vs practice + generator workflow | 2100 | 8 | Core SEO tool traffic | Link SEO checklist; do not rewrite full SEO guide | todo
W3-01 | 3 | 5 | P0 | Best Free YouTube Title Generators 2026 (Tested Workflows) | youtube title generator free | ai youtube title generator, best title generator youtube, free title ideas youtube | commercial | 3K–12K | $2–$6 | $2.50–$6 | ai-tools | /tools/youtube-title-generator | /tools/youtube-title-ab-tester; /tools/vs/vidiq | Comparison + why free browser tools win for drafts | 2300 | 7 | Commercial listicle capturing tool keyword | Position YTTH as free no-extension option | todo
W3-02 | 3 | 5 | P1 | ElevenLabs for YouTube: Voiceover Workflow (Faceless-Friendly) | elevenlabs youtube | elevenlabs tutorial youtube, ai voiceover youtube, elevenlabs for faceless channel | commercial | 2K–8K | $4–$10 | $3–$8 | ai-tools | /tools/youtube-shorts-script-planner | /tools/youtube-intro-script-generator; /blog/faceless-youtube-channel-ideas-2026 | Tutorial workflow + ethics/disclosure notes | 2400 | 7 | High CPC AI software intent; faceless cluster | Do not clone generic AI tools list posts | todo
W3-03 | 3 | 5 | P1 | CapCut vs DaVinci Resolve for YouTube: Which Should You Use? | capcut vs davinci resolve | best free editor youtube, capcut for youtube, davinci resolve youtube | commercial | 1K–5K | $3–$8 | $3–$7 | software | /tools/youtube-shorts-script-planner | /blog/best-free-video-editors-youtube-2026; /blog/davinci-resolve-tutorial-youtube-beginners | Honest comparison table by use case | 2200 | 6 | Comparison CPC; links existing editor content | Comparison not full tutorial rewrite | todo
W3-04 | 3 | 6 | P1 | Best Budget YouTube Studio Setup Under $300 (US Shopping List) | budget youtube studio setup | youtube setup on a budget, cheap youtube equipment, starter youtube studio | commercial | 2K–8K | $3–$9 | $3–$8 | equipment | /tools/youtube-banner-logo-maker | /blog/ultimate-youtube-equipment-checklist-2026; /tools/youtube-niche-finder-quiz | Shopping tiers + mic/light/camera priorities | 2500 | 7 | Shopping intent = higher CPC ads | Narrow under-$300 angle vs full equipment checklist | todo
W3-05 | 3 | 6 | P1 | USB Mic vs Lavalier for YouTube: Which Sounds Better for Talking Heads? | usb mic vs lavalier youtube | best mic for youtube talking head, lavalier vs usb microphone | commercial | 1K–4K | $4–$10 | $3–$8 | equipment | /tools/youtube-channel-audit | /blog/best-usb-microphones-youtube-podcasting-2026; /blog/best-wireless-lavalier-microphones-youtube | Use-case verdict + link existing mic reviews | 2000 | 6 | Product comparison CPC | Comparison hub linking mic listicles | todo
W3-06 | 3 | 6 | P2 | YouTube Live Streaming Setup Checklist (First Stream Without Panic) | youtube live streaming setup | youtube live checklist, go live on youtube setup, youtube streaming equipment basic | informational-commercial | 2K–8K | $2–$6 | $2–$5 | growth | /tools/youtube-channel-audit | /tools/youtube-title-generator; /blog/obs-studio-youtube-setup | Checklist + OBS link | 2100 | 7 | Setup intent; gear ads | Link OBS post; do not rewrite full OBS guide | todo
W4-01 | 4 | 7 | P0 | YouTube CTR Optimization 2026: Data-Backed Ways to Improve Click Rate | youtube ctr optimization | improve youtube ctr, good youtube ctr, youtube click through rate tips | informational | 2K–8K | $2–$6 | $2–$5 | growth | /tools/youtube-title-ab-tester | /tools/youtube-thumbnail-downloader; /tools/youtube-title-generator | Benchmarks + packaging experiments | 2300 | 8 | Core growth; tool pairing for titles/thumbs | Link algorithm guide; packaging focus only | todo
W4-02 | 4 | 7 | P1 | YouTube Hook Examples: 20 First-30-Second Openings by Niche | youtube hook examples | youtube intro examples, first 30 seconds youtube, video hook script | informational | 2K–8K | $1–$4 | $1.50–$4 | content-strategy | /tools/youtube-intro-script-generator | /tools/youtube-shorts-script-planner; /tools/youtube-video-ideas-generator | 20 examples + generator workflow | 2200 | 6 | High save/share potential; script tools | Examples-focused vs script formula post | todo
W4-03 | 4 | 7 | P1 | YouTube Content Calendar Template: Plan 4 Weeks of Videos (Free) | youtube content calendar template | youtube content planner, content calendar for youtube, youtube posting schedule template | informational | 2K–8K | $1.50–$4.50 | $2–$5 | content-strategy | /tools/youtube-content-calendar-generator | /tools/youtube-video-ideas-generator; /blog/youtube-content-batching | Template table + generator CTA | 2000 | 6 | Template traffic + calendar tool | Link batching post | todo
W4-04 | 4 | 8 | P1 | YouTube Competitor Analysis: Repeatable Research Workflow | youtube competitor analysis | analyze youtube competitors, youtube competitor research, spy on youtube channels | informational-commercial | 1K–5K | $2–$6 | $2–$5 | growth | /tools/youtube-tag-extractor | /tools/youtube-subscriber-count-checker; /tools/youtube-thumbnail-downloader | Workflow + free tools stack | 2200 | 7 | Research intent; multiple tool CTAs | Unique workflow doc | todo
W4-05 | 4 | 8 | P1 | YouTube Playlist Strategy: Increase Session Watch Time | youtube playlist strategy | youtube playlists for growth, playlist seo youtube, organize youtube playlists | informational | 1K–4K | $1–$3.50 | $1.50–$4 | growth | /tools/youtube-playlist-length-calculator | /tools/youtube-timestamp-generator; /tools/youtube-description-generator | Strategy + playlist length tool | 1900 | 6 | Watch-time growth; underused tool | New dedicated strategy post | todo
W4-06 | 4 | 8 | P2 | YouTube Shorts Ideas That Lead to Long-Form Views | youtube shorts ideas that get views | shorts to long form strategy, youtube shorts funnel, shorts ideas 2026 | informational | 3K–12K | $1–$3.50 | $1.50–$4 | shorts | /tools/youtube-shorts-script-planner | /tools/youtube-video-ideas-generator; /blog/youtube-shorts-monetization-2026 | Idea formulas + funnel to long-form | 2100 | 7 | Volume + Shorts planner; monetization realism | Funnel angle vs pure ideas/monetization posts | todo
W5-01 | 5 | 9 | P1 | How to Start a Finance YouTube Channel in 2026 (Realistic Plan) | how to start a finance youtube channel | finance youtube niche, personal finance youtube, investing youtube channel | commercial | 1K–5K | $5–$14 | $4–$10 | niches | /tools/youtube-niche-finder-quiz | /tools/youtube-earnings-calculator; /resources/youtube-cpm-rates | Realistic plan; NO $50k promises; compliance note | 2600 | 8 | High RPM niche; finance ads | Honest tone vs hype “$50k blueprint” style | todo
W5-02 | 5 | 9 | P1 | How to Start a Tech Review YouTube Channel (Gear + SEO Basics) | how to start a tech youtube channel | tech review youtube, gadget channel startup, youtube tech niche | commercial | 1K–5K | $3–$9 | $3–$7 | niches | /tools/youtube-video-ideas-generator | /tools/youtube-title-generator; /tools/youtube-tag-generator | Startup plan + affiliate note | 2400 | 7 | Tech ads CPC; review intent | New niche hub page | todo
W5-03 | 5 | 9 | P2 | How to Start a Fitness YouTube Channel Without Expensive Gear | how to start a fitness youtube channel | workout youtube channel, fitness channel tips, home workout youtube | informational-commercial | 2K–8K | $2–$7 | $2–$6 | niches | /tools/youtube-content-calendar-generator | /tools/youtube-channel-name-generator; /tools/youtube-banner-logo-maker | Beginner plan + disclaimers | 2300 | 7 | Volume niche + brand ads | New | todo
W5-04 | 5 | 10 | P1 | YouTube Podcast Setup: Film Once, Publish Audio + Video | youtube podcast setup | podcast on youtube, youtube podcast tips, start podcast youtube | commercial | 2K–8K | $2–$7 | $2–$6 | niches | /tools/youtube-timestamp-generator | /tools/youtube-description-generator; /blog/best-usb-microphones-youtube-podcasting-2026 | Setup + dual publish workflow | 2300 | 7 | Podcast+YouTube growth; mic ads | New | todo
W5-05 | 5 | 10 | P2 | Faceless Cooking Channel Ideas That Are Actually Filmable | faceless cooking youtube channel | cooking channel without face, recipe youtube faceless, food youtube automation | informational | 1K–4K | $1.50–$5 | $2–$5 | niches | /tools/youtube-video-ideas-generator | /blog/faceless-youtube-channel-ideas-2026; /tools/youtube-shorts-script-planner | Filmable ideas + production notes | 2100 | 6 | Faceless + niche volume | Niche-specific vs general faceless lists | todo
W5-06 | 5 | 10 | P2 | Travel Vlog on a Budget: Gear, Style & Monetization Reality Check | travel vlog youtube guide | start travel youtube channel, travel vlog tips, travel youtube monetization | informational-commercial | 2K–8K | $2–$7 | $2–$6 | niches | /tools/youtube-earnings-calculator | /resources/youtube-cpm-rates; /tools/youtube-content-calendar-generator | Budget plan + honest RPM | 2400 | 7 | Travel commercial ads + gear | New | todo
W6-01 | 6 | 11 | P0 | YouTube Analytics Metrics That Matter (Ignore the Vanity Ones) | youtube analytics metrics explained | youtube studio metrics, which youtube metrics matter, youtube analytics guide | informational | 2K–8K | $2–$6 | $2–$5 | analytics | /tools/youtube-engagement-rate-calculator | /tools/youtube-channel-audit; /blog/youtube-analytics-guide-beginners-2026 | Metric dictionary + actions | 2300 | 8 | Studio intent; engagement tool | Deeper metrics focus than beginner walkthrough | todo
W6-02 | 6 | 11 | P1 | YouTube End Screen Best Practices 2026 (Layouts That Don’t Annoy) | youtube end screen best practices | youtube end screens, end screen layout, youtube end screen tips | informational | 1K–4K | $1–$3.50 | $1.50–$4 | growth | /tools/youtube-channel-audit | /tools/youtube-video-ideas-generator | Layouts + timing | 1800 | 6 | Session growth; low competition angle | New | todo
W6-03 | 6 | 11 | P1 | YouTube Community Posts Strategy: Get Views Without a New Video | youtube community posts strategy | youtube community tab tips, community posts for growth, youtube polls strategy | informational | 1K–4K | $1–$3.50 | $1.50–$4 | growth | /tools/youtube-video-ideas-generator | /tools/youtube-content-calendar-generator | Post types + cadence | 1900 | 6 | Engagement growth content | New | todo
W6-04 | 6 | 12 | P1 | YouTube Traffic Sources Explained: Browse, Search, Suggested, Shorts | youtube traffic sources | youtube browse features, youtube suggested videos, youtube search traffic | informational | 2K–8K | $1.50–$4 | $2–$5 | growth | /tools/youtube-channel-audit | /resources/youtube-algorithm-guide; /tools/youtube-tag-generator | Source-by-source tactics | 2200 | 7 | Algorithm adjacent; high learning intent | Link algorithm guide as pillar | todo
W6-05 | 6 | 12 | P2 | How to Use a Free TubeBuddy Alternative (No Extension Workflow) | free tubebuddy alternative no extension | tubebuddy free alternative, youtube tools without extension, vidiq alternative free | commercial | 1K–5K | $3–$8 | $3–$7 | ai-tools | /tools | /tools/vs/tubebuddy; /tools/vs/vidiq; /tools/youtube-tag-generator | Workflow map tool-by-tool | 2100 | 7 | Direct competitor keywords; brand capture | Complements vs pages | todo
W6-06 | 6 | 12 | P0 | YouTube Comment Giveaway Rules That Stay Fair (Plus Free Picker) | youtube comment giveaway | youtube giveaway picker, random comment winner, youtube contest rules | informational | 2K–8K | $1–$3.50 | $1.50–$4 | growth | /tools/youtube-comment-picker | /tools/youtube-engagement-rate-calculator | Rules + fairness + tool | 1900 | 7 | Direct match for comment picker volume | Policy-safe giveaway focus | todo

## 12-Week Calendar
Week | Wave | Publish 1 (Mon) | Publish 2 (Wed) | Publish 3 (Fri) | Refresh (any day)
1 | 1 | W1-01: YouTube Sponsorship Rates 2026: How Much Brands Pay Creators | W1-02: YouTube AdSense RPM Optimization: 12 Ways to Raise Revenue Per 1,000 Views | W1-03: YouTube Media Kit Examples 2026: 7 Templates Brands Actually Open | /resources/youtube-cpm-rates — Update data date, add methodology note, 2 internal links to country calculators
2 | 1 | W1-04: Best YouTube Affiliate Programs 2026 (High Commission, Creator-Friendly) | W1-05: How Much Do YouTubers Make Per Video in 2026? (Views × RPM Examples) | W1-06: YouTube Brand Deal Email Template: Outreach That Gets Replies | /tools/youtube-earnings-calculator — Add 2026 Q&A, link new sponsorship + RPM posts when live
3 | 2 | W2-01: YouTube Thumbnail Size 2026: Exact Specs, Safe Zones & File Rules | W2-02: How to Download a YouTube Thumbnail in Highest Quality (HD/4K) | W2-03: YouTube Description Template 2026: Copy, Customize, Rank | /blog/youtube-media-kit-template-2026 — Add example screenshots section + link W1-03
4 | 2 | W2-04: YouTube Chapters Template: Timestamp Format That Works in 2026 | W2-05: YouTube Channel Name Ideas: Framework by Niche (With Generator Workflow) | W2-06: YouTube Tags Explained 2026: How Many Tags, What Works, What Doesn’t | /blog/youtube-thumbnail-design-psychology — Add size specs + downloader CTA
5 | 3 | W3-01: Best Free YouTube Title Generators 2026 (Tested Workflows) | W3-02: ElevenLabs for YouTube: Voiceover Workflow (Faceless-Friendly) | W3-03: CapCut vs DaVinci Resolve for YouTube: Which Should You Use? | /blog/youtube-seo-checklist-2026 — Consolidate tag advice; link tag generator/extractor
6 | 3 | W3-04: Best Budget YouTube Studio Setup Under $300 (US Shopping List) | W3-05: USB Mic vs Lavalier for YouTube: Which Sounds Better for Talking Heads? | W3-06: YouTube Live Streaming Setup Checklist (First Stream Without Panic) | /resources/youtube-monetization-guide — Add AdSense payment + RPM internal links
7 | 4 | W4-01: YouTube CTR Optimization 2026: Data-Backed Ways to Improve Click Rate | W4-02: YouTube Hook Examples: 20 First-30-Second Openings by Niche | W4-03: YouTube Content Calendar Template: Plan 4 Weeks of Videos (Free) | /blog/youtube-shorts-monetization-2026 — Update Shorts vs long-form RPM table
8 | 4 | W4-04: YouTube Competitor Analysis: Repeatable Research Workflow | W4-05: YouTube Playlist Strategy: Increase Session Watch Time | W4-06: YouTube Shorts Ideas That Lead to Long-Form Views | /blog/get-1000-subscribers-youtube-fast-2026 — Add 90-day worksheet + tool CTAs
9 | 5 | W5-01: How to Start a Finance YouTube Channel in 2026 (Realistic Plan) | W5-02: How to Start a Tech Review YouTube Channel (Gear + SEO Basics) | W5-03: How to Start a Fitness YouTube Channel Without Expensive Gear | /blog/faceless-youtube-channel-ideas-2026 — Add filmable production notes; prune hype
10 | 5 | W5-04: YouTube Podcast Setup: Film Once, Publish Audio + Video | W5-05: Faceless Cooking Channel Ideas That Are Actually Filmable | W5-06: Travel Vlog on a Budget: Gear, Style & Monetization Reality Check | /tools/vs/tubebuddy — Refresh comparison vs free suite 2026
11 | 6 | W6-01: YouTube Analytics Metrics That Matter (Ignore the Vanity Ones) | W6-02: YouTube End Screen Best Practices 2026 (Layouts That Don’t Annoy) | W6-03: YouTube Community Posts Strategy: Get Views Without a New Video | /blog/youtube-algorithm-guide-2026 — Update ranking factors summary + speakable block
12 | 6 | W6-04: YouTube Traffic Sources Explained: Browse, Search, Suggested, Shorts | W6-05: How to Use a Free TubeBuddy Alternative (No Extension Workflow) | W6-06: YouTube Comment Giveaway Rules That Stay Fair (Plus Free Picker) | /blog/how-much-youtube-pays-per-1000-views-2026 — Align numbers with cpm-data.ts + calculator

## Refresh Queue
Week | Existing URL | Refresh Action | Status
1 | /resources/youtube-cpm-rates | Update data date, add methodology note, 2 internal links to country calculators | todo
2 | /tools/youtube-earnings-calculator | Add 2026 Q&A, link new sponsorship + RPM posts when live | todo
3 | /blog/youtube-media-kit-template-2026 | Add example screenshots section + link W1-03 | todo
4 | /blog/youtube-thumbnail-design-psychology | Add size specs + downloader CTA | todo
5 | /blog/youtube-seo-checklist-2026 | Consolidate tag advice; link tag generator/extractor | todo
6 | /resources/youtube-monetization-guide | Add AdSense payment + RPM internal links | todo
7 | /blog/youtube-shorts-monetization-2026 | Update Shorts vs long-form RPM table | todo
8 | /blog/get-1000-subscribers-youtube-fast-2026 | Add 90-day worksheet + tool CTAs | todo
9 | /blog/faceless-youtube-channel-ideas-2026 | Add filmable production notes; prune hype | todo
10 | /tools/vs/tubebuddy | Refresh comparison vs free suite 2026 | todo
11 | /blog/youtube-algorithm-guide-2026 | Update ranking factors summary + speakable block | todo
12 | /blog/how-much-youtube-pays-per-1000-views-2026 | Align numbers with cpm-data.ts + calculator | todo

## Tool CTA Map
Tool Path | Linked New Post IDs | Role
/tools/youtube-earnings-calculator | W1-01, W1-02, W1-05, W5-06 | Primary CTA hub
/tools/youtube-engagement-rate-calculator | W1-03, W1-06, W6-01 | Primary CTA hub
/tools/youtube-video-ideas-generator | W1-04, W5-02, W5-05, W6-03 | Primary CTA hub
/tools/youtube-thumbnail-downloader | W2-01, W2-02 | Primary CTA hub
/tools/youtube-description-generator | W2-03 | Primary CTA hub
/tools/youtube-timestamp-generator | W2-04, W5-04 | Primary CTA hub
/tools/youtube-channel-name-generator | W2-05 | Primary CTA hub
/tools/youtube-tag-generator | W2-06 | Primary CTA hub
/tools/youtube-title-generator | W3-01 | Primary CTA hub
/tools/youtube-shorts-script-planner | W3-02, W3-03, W4-06 | Primary CTA hub
/tools/youtube-banner-logo-maker | W3-04 | Primary CTA hub
/tools/youtube-channel-audit | W3-05, W3-06, W6-02, W6-04 | Primary CTA hub
/tools/youtube-title-ab-tester | W4-01 | Primary CTA hub
/tools/youtube-intro-script-generator | W4-02 | Primary CTA hub
/tools/youtube-content-calendar-generator | W4-03, W5-03 | Primary CTA hub
/tools/youtube-tag-extractor | W4-04 | Primary CTA hub
/tools/youtube-playlist-length-calculator | W4-05 | Primary CTA hub
/tools/youtube-niche-finder-quiz | W5-01 | Primary CTA hub
/tools | W6-05 | Primary CTA hub
/tools/youtube-comment-picker | W6-06 | Primary CTA hub

## Do Not Publish
Topic | Reason | Action
LLC vs sole proprietor tax advice (jurisdiction-specific) | YMYL; needs qualified author | Delay or hire expert
Best tax software absolute recommendations as legal advice | YMYL | Delay or general overview only
Guaranteed $10k/$50k/month income claims | Trust + policy risk | Never publish
New title generator tool page | Tool already live at /tools/youtube-title-generator | Publish blog, not new tool
New money calculator at /youtube-money-calculator | Use existing earnings calculator | 301 already if needed
Duplicate algorithm 2026 explainers | Multiple algorithm posts exist | Refresh pillar only
Duplicate faceless idea listicles | Already consolidated | Refresh canonical only

## Live Inventory Snapshot
# | Live Blog Slug | Suggested action
1 | youtube-media-kit-template-2026 | OK as sibling if keyword differs
2 | youtube-adsense-payment-schedule-2026 | OK as sibling if keyword differs
3 | youtube-algorithm-guide-2026 | Prefer refresh over new similar post
4 | ultimate-youtube-equipment-checklist-2026 | OK as sibling if keyword differs
5 | obs-studio-youtube-setup | OK as sibling if keyword differs
6 | best-webcam-youtube-streaming | OK as sibling if keyword differs
7 | best-wireless-lavalier-microphones-youtube | OK as sibling if keyword differs
8 | ai-subtitle-generator-youtube | OK as sibling if keyword differs
9 | descript-youtube-editing | OK as sibling if keyword differs
10 | youtube-super-thanks-earnings | OK as sibling if keyword differs
11 | youtube-content-batching | OK as sibling if keyword differs
12 | youtube-subscriber-milestones | OK as sibling if keyword differs
13 | youtube-shorts-best-editing-apps-techniques | OK as sibling if keyword differs
14 | youtube-seo-checklist-2026 | OK as sibling if keyword differs
15 | youtube-studio-walkthrough | OK as sibling if keyword differs
16 | ai-scriptwriting-tools-youtube | OK as sibling if keyword differs
17 | shorts-vs-reels-vs-tiktok-pay | OK as sibling if keyword differs
18 | youtube-music-copyright-guide | OK as sibling if keyword differs
19 | gaming-youtube-growth-strategies-2026 | OK as sibling if keyword differs
20 | best-video-editing-laptops-2026 | OK as sibling if keyword differs
21 | opus-clip-tutorial | OK as sibling if keyword differs
22 | how-to-get-more-views-youtube-2026 | OK as sibling if keyword differs
23 | best-time-upload-youtube-2026 | OK as sibling if keyword differs
24 | best-youtube-niches-2026 | OK as sibling if keyword differs
25 | ai-video-generators-youtube-shorts-2026 | OK as sibling if keyword differs
26 | get-1000-subscribers-youtube-fast-2026 | OK as sibling if keyword differs
27 | youtube-automation-complete-guide-2026 | OK as sibling if keyword differs
28 | high-cpm-youtube-niches-2026 | OK as sibling if keyword differs
29 | youtube-pay-per-view-2026 | OK as sibling if keyword differs
30 | tubebuddy-vs-vidiq-2026 | OK as sibling if keyword differs
31 | youtube-keyword-research-tools-2026 | OK as sibling if keyword differs
32 | ai-thumbnail-generators-youtube-2026 | OK as sibling if keyword differs
33 | youtube-shorts-monetization-2026 | Prefer refresh over new similar post
34 | youtube-shorts-ideas-2026 | OK as sibling if keyword differs
35 | youtube-partner-program-2026 | OK as sibling if keyword differs
36 | faceless-youtube-channel-2026 | Prefer refresh over new similar post
37 | youtube-algorithm-2026 | Prefer refresh over new similar post
38 | best-ai-video-editing-software-2026 | OK as sibling if keyword differs
39 | chatgpt-youtube-content-creation | OK as sibling if keyword differs
40 | faceless-youtube-channel-ideas-2026 | Prefer refresh over new similar post
41 | youtube-money-per-subscriber-2026 | OK as sibling if keyword differs
42 | best-enterprise-ai-platforms-2026 | OK as sibling if keyword differs
43 | youtube-vs-tiktok-money-2026 | OK as sibling if keyword differs
44 | youtube-monetization-guide-2026 | Prefer refresh over new similar post
45 | youtube-tax-guide-creators-usa-2026 | OK as sibling if keyword differs
46 | how-to-start-youtube-business-2026 | OK as sibling if keyword differs
47 | youtube-rpm-vs-cpm-explained | OK as sibling if keyword differs
48 | how-youtubers-get-paid-complete-guide | OK as sibling if keyword differs
49 | youtube-automation-ai-tools-2026 | OK as sibling if keyword differs
50 | youtube-sponsorship-guidelines-2026 | OK as sibling if keyword differs
51 | youtube-shorts-domination-2026 | OK as sibling if keyword differs
52 | ai-tools-youtube-creators-2026 | OK as sibling if keyword differs
53 | youtube-thumbnail-design-psychology | OK as sibling if keyword differs
54 | youtube-algorithm-secrets-2026 | Prefer refresh over new similar post
55 | faceless-youtube-channel-blueprint | Prefer refresh over new similar post
56 | youtube-monetization-complete-guide-2026 | Prefer refresh over new similar post
57 | youtube-video-ideas-that-actually-work | OK as sibling if keyword differs
58 | best-youtube-tools-for-beginners | OK as sibling if keyword differs
59 | how-to-write-catchy-youtube-titles | OK as sibling if keyword differs
60 | how-to-optimize-youtube-thumbnails | OK as sibling if keyword differs
61 | youtube-seo-basics-archived | OK as sibling if keyword differs
62 | grow-youtube-channel-fast | OK as sibling if keyword differs
63 | how-to-get-1000-subscribers-and-10000-views | OK as sibling if keyword differs
64 | youtube-script-formula-retention | OK as sibling if keyword differs
65 | youtube-monetization-truths-cpm-rpm | Prefer refresh over new similar post
66 | youtube-automation-tools-guide | OK as sibling if keyword differs
67 | youtube-seo-complete-guide | OK as sibling if keyword differs
68 | youtube-shorts-viral-strategy-2026 | OK as sibling if keyword differs
69 | youtube-analytics-guide-beginners-2026 | OK as sibling if keyword differs
70 | how-much-youtube-pays-per-1000-views-2026 | OK as sibling if keyword differs
71 | youtube-cpm-rates-by-country-2026 | OK as sibling if keyword differs
72 | youtube-partner-program-requirements-2026 | OK as sibling if keyword differs
73 | best-ai-tools-youtube-creators-2026 | OK as sibling if keyword differs
74 | most-profitable-youtube-niches-2026 | OK as sibling if keyword differs
75 | 25-best-ai-tools-for-youtube-creators | OK as sibling if keyword differs
76 | best-youtube-seo-tools-2026 | OK as sibling if keyword differs
77 | best-free-youtube-intro-makers-2026 | OK as sibling if keyword differs
78 | free-midjourney-alternatives-2026 | OK as sibling if keyword differs
79 | best-free-video-editors-youtube-2026 | OK as sibling if keyword differs
80 | best-mobile-video-editing-apps-no-watermark | OK as sibling if keyword differs
81 | canva-ai-tools-youtube-complete-tutorial | OK as sibling if keyword differs
82 | youtube-memberships-pricing-setup-guide | OK as sibling if keyword differs
83 | best-microphones-under-100-youtube | OK as sibling if keyword differs
84 | youtube-banner-makers-2026 | OK as sibling if keyword differs
85 | capcut-ai-features-complete-youtube-editing-guide | OK as sibling if keyword differs
86 | best-4k-cameras-under-1000-vlogging-2026 | OK as sibling if keyword differs
87 | best-usb-microphones-youtube-podcasting-2026 | OK as sibling if keyword differs
88 | davinci-resolve-tutorial-youtube-beginners | OK as sibling if keyword differs
89 | youtube-channel-branding-guide | OK as sibling if keyword differs
90 | youtube-thumbnail-ab-testing-guide-2026 | OK as sibling if keyword differs
91 | best-budget-youtube-cameras-under-500 | OK as sibling if keyword differs
92 | lawyer-youtube-marketing | OK as sibling if keyword differs
93 | how-to-start-youtube-channel-2026 | OK as sibling if keyword differs
94 | how-to-rank-on-ai-search-chatgpt-perplexity-gemini-2026 | OK as sibling if keyword differs
95 | insurance-youtube-marketing | OK as sibling if keyword differs

## Writing Rules
Rule | Detail
Primary keyword | One primary keyword per URL; check GSC first for existing rankings
Answer first | 40–80 word answer in first 100 words (AEO / snippets)
Length | 1,800–2,800 words for most; money posts 2,200+
FAQ | 6–8 PAA-style Q&As + FAQ schema
Tool CTA | 1 primary tool in intro + mid + end; only if relevant
Internal links | 2–4 contextual links to pillars/tools/siblings
US Tier-1 | USD examples, US products when natural
No hype income | No guaranteed $10k/month claims
YMYL | Tax/legal/medical: delay or expert review
Images | One original chart/table when possible; descriptive alt text
Update date | Show last reviewed on data posts
After publish | IndexNow + GSC request; add to cluster links if needed
Deploy | Site must be on latest Hostinger build for new URLs to work

## Revenue Reality
REALISTIC revenue framing (not the old 60k PV month-1 model)
Formula | Monthly AdSense ≈ (pageviews / 1000) × page RPM
Scenario | Monthly organic PV | RPM | AdSense/mo
Now-ish | 500–2,000 | $1.50–$3 | $1–$6
After 3 mo good publish | 3,000–8,000 | $2.50–$5 | $8–$40
After 6–12 mo + links | 15,000–50,000 | $3–$7 | $45–$350
Notes
CPC in sheet = advertiser PPC CPC (directional), NOT your AdSense CPC
RPM rises mainly with US/UK/CA/AU share + commercial topics
Affiliate revenue needs separate programs + disclosures — not assumed